## RMS
Screen/Function | Description | Planned-In | In Charge | Done-In | RDS | Status | Updated | Update Details | Update Details | Note
ManageUsers_Add | As an admin, I want to create a new user account and assign a role. | Iteration 1 | Thành | Iteration 1 |  | Done | Not Yet
ViewRoomList | As a guest, I want to browse the list of available rooms so I can choose a suitable room. | Level 2 |  | Iteration 3 |  | Iteration 1 | II.2.1; III.1.1.a | To Do |  | Not Yet
ManageUsers_Delete | As an admin, I want to deactivate or delete a user account. | Iteration 1 | Thành | Iteration 1 |  | Done | Not Yet
ManageUsers_Role | As an admin, I want to assign roles (Admin/Doctor/Staff/Receptionist/Patient) to users. | Iteration 1 | Thành | Iteration 1 |  | Done | Not Yet
ManageDoctors_List | As an admin, I want to view all doctors and their specialty. | Iteration 1 | Thành | Iteration 1 |  | Done | Not Yet
ManageDoctors_Add | As an admin, I want to add a new doctor profile with specialty. | Iteration 1 | Thành | Iteration 1 |  | Done | Not Yet
ManageDoctors_Edit | As an admin, I want to edit doctor profile details. | Iteration 1 | Thành | Iteration 1 |  | Done | Not Yet
SystemLog_View | As an admin, I want to view a system audit log of all critical operations. | Iteration 1 | Thành | Iteration 1 |  | Done | Not Yet
SystemLog_Filter | As an admin, I want to filter logs by user, action type, and date range. | Iteration 1 | Thành | Iteration 1 |  | Done | Not Yet
PatientRecord_Create | As medical staff, I want to create a new patient medical record in the system. | Iteration 1 | Quỳnh | Iteration 1 |  | Done | Not Yet
PatientRecord_View | As medical staff, I want to view a patient's complete medical record. | Iteration 1 | Quỳnh | Iteration 1 |  | Done | Not Yet
PatientRecord_Update | As medical staff, I want to update patient record data. | Iteration 1 | Quỳnh | Iteration 1 |  | Done | Not Yet
PatientRecord_Store | As medical staff, I want to securely store and archive patient records. | Iteration 1 | Quỳnh | Iteration 1 |  | Done | Not Yet
Auth_Login | As a user, I want to log in with email/phone and password. | Iteration 1 | Nam | Iteration 1 |  | Done | Not Yet
Auth_Register | As a new user, I want to register an account using email or phone number. | Iteration 1 | Nam | Iteration 1 |  | Done | Not Yet
Auth_GoogleSSO | As a user, I want to log in or register using my Google account. | Iteration 1 | Nam | Iteration 1 |  | Done | Not Yet
Auth_ForgotPassword | As a user, I want to reset my password via email/phone. | Iteration 1 | Nam | Iteration 1 |  | Done | Not Yet
AI_Setup | Set up FastAPI AI service (separate from Java Servlet/JSP), define AIRequest/AIResponse DTOs. | Iteration 1 | Nam | Iteration 1 |  | Done | Not Yet
AI_TrainModel | Train Random Forest on Diabetes dataset (920 patients, 13 features); save model artifacts. | Iteration 1 | Nam | Iteration 1 |  | Done | Not Yet
Patient_Register | As a patient, I want to register a personal account via the mobile app so that I can access the cardio healthcare system | Iteration 1 | Đức Anh | Iteration 1 |  | Done | Not Yet
Patient_Login | As a patient, I want to log in securely to my account so that I can manage my health records safely. | Iteration 1 | Đức Anh | Iteration 1 |  | Done | Not Yet
Patient_UpdateInfo | As a patient, I want to update my personal information (phone, address, email) so that the clinic can contact me in case of emergency. | Iteration 1 | Đức Anh | Iteration 1 |  | Done | Not Yet
RegisterPatient | As a receptionist, I want to register a new patient with full personal information. | Iteration 2 | Thành | Iteration 2 |  | Doing | Not Yet
UpdatePatient_Basic | As a receptionist, I want to update basic patient contact information. | Iteration 2 | Thành | Iteration 2 |  | Doing | Not Yet
Appointment_Create | As a receptionist, I want to create a new appointment for a patient with a doctor. | Iteration 2 | Thành | Iteration 2 |  | Doing | Not Yet
Appointment_UpdateStatus | As a receptionist, I want to update appointment status (Confirmed/Cancelled/Rescheduled). | Iteration 2 | Thành | Iteration 2 |  | Doing | Not Yet
Appointment_ViewCalendar | As staff, I want to view the appointment calendar by day/week. | Iteration 2 | Thành | Iteration 2 |  | Doing | Not Yet
Reports_System | As an admin, I want to view system reports (patient activity, appointments, access history). | Iteration 2 | Thành | Iteration 2 |  | Doing | Not Yet
RecordVitalSigns | As medical staff, I want to record vital signs (BP, heart rate, temperature, SpO2) per visit. | Iteration 2 | Quỳnh | Iteration 2 |  | Doing | Not Yet
UploadTestResults | As medical staff, I want to upload lab/imaging results (blood, urine, X-ray, MRI, CT, ultrasound). | Iteration 2 | Quỳnh | Iteration 2 |  | Doing | Not Yet
Vitals_History | As medical staff, I want to view a patient's historical vital signs across visits. | Iteration 2 | Quỳnh | Iteration 2 |  | Doing | Not Yet
TestResult_View | As medical staff, I want to view previously uploaded test results for a patient. | Iteration 2 | Quỳnh | Iteration 2 |  | Doing | Not Yet
Doctor_ViewPatientList | As a doctor, I want to view my assigned patients via GeneralExaminationListServlet (dao.getGeneralExaminationRecords) and ExaminationListServlet (dao.getDetailedExaminationRecords). | Iteration 2 | Nam | Iteration 2 |  | Done | Not Yet
Doctor_ViewPatientDetail | As a doctor, I want to view detailed patient profile and examination history via DetailServlet (dao.getHealthRecordById). | Iteration 2 | Nam | Iteration 2 |  | Done | Not Yet
Doctor_StartConsultation | As a doctor, I want to accept an appointment and start consultation via AcceptRecordServlet (dao.acceptAppointment). | Iteration 2 | Nam | Iteration 2 |  | Done | Not Yet
Doctor_CompleteConsult | As a doctor, I want to complete a consultation and finalise the visit record via saveMedicalRecordAndCompleteForDoctor. | Iteration 2 | Nam | Iteration 2 |  | Done | Not Yet
Doctor_EnterDiagnosis | As a doctor, I want to add diagnoses per consultation via saveMedicalRecordAndCompleteForDoctor. | Iteration 2 | Nam | Iteration 2 |  | Done | Not Yet
Doctor_UpdateNotes | As a doctor, I want to update clinical notes and treatment plan via updateMedicalRecord. | Iteration 2 | Nam | Iteration 2 |  | Done | Not Yet
AI_Predict | As a doctor, I want to run AI diabetes prediction using /predict endpoint and view the probabilities. | Iteration 2 | Nam | Iteration 2 |  | Done | Not Yet
AI_SHAPExplain | As a doctor, I want to get clinical advice/explanations in Vietnamese via GeminiIntegration.getChatResponse. | Iteration 2 | Nam | Iteration 2 |  | Done | Not Yet
AI_TrendAnalysis | As a doctor, I want to view diabetes indicators (hba1c, glucose) trend across consultations. | Iteration 2 | Nam | Iteration 2 |  | Done | Not Yet
AI_SavePrediction | Save AI prediction (normal, pre-diabetes, diabetes probabilities) to database via dao.saveAiResults. | Iteration 2 | Nam | Iteration 2 |  | Done | Not Yet
Patient_ViewAppointment | As a patient, I want to view my upcoming and past appointments so that I can manage my clinical visits easily | Iteration 2 | Đức Anh | Iteration 2 |  | Doing | Not Yet
Patient_SubmitSymptoms | As a patient, I want to submit my cardiovascular metrics (blood pressure, heart rate, cholesterol, chest pain) so that the AI model can analyze my heart risk level | Iteration 2 | Đức Anh | Iteration 2 |  | Doing | Not Yet
Patient_ViewAlerts | As a patient, I want to view health alerts directly relevant to me. | Iteration 2 | Đức Anh | Iteration 2 |  | Doing | Not Yet
ManageUsers_Search | As an admin, I want to search and filter users by role, status, and name. | Iteration 3 | Thành | Iteration 3 |  | To Do | Not Yet
ManageDoctors_Specialty | As an admin, I want to distinguish and manage general vs specialist doctors. | Iteration 3 | Thành | Iteration 3 |  | To Do | Not Yet
Reports_Advanced | As an admin, I want advanced reports: risk distribution, alert stats, AI usage. | Iteration 3 | Thành | Iteration 3 |  | To Do | Not Yet
Appointment_Reschedule | As a receptionist, I want to reschedule an existing appointment and notify the patient. | Iteration 3 | Thành | Iteration 3 |  | To Do | Not Yet
Appointment_Search | As a receptionist, I want to search appointments by patient name, date, or doctor. | Iteration 3 | Thành | Iteration 3 |  | To Do | Not Yet
Test_AdminReports | Test all admin report functions with realistic multi-user data. | Iteration 3 | Thành | Iteration 3 |  | To Do | Not Yet
Alert_AutoTrigger | System auto-creates alerts when a patient's vitals exceed configured thresholds (BR checkAndCreateAlert). | Iteration 3 | Quỳnh | Iteration 3 |  | To Do | Not Yet
Vitals_RangeValidation | Add physiological range validation when entering vitals to flag abnormal inputs at the API layer. | Iteration 3 | Quỳnh | Iteration 3 |  | To Do | Not Yet
TestResult_Download | As medical staff, I want to download previously uploaded test result files. | Iteration 3 | Quỳnh | Iteration 3 |  | To Do | Not Yet
Test_VitalsEdgeCases | Test vital sign entry with extreme/missing values and validate alert triggers. | Iteration 3 | Quỳnh | Iteration 3 |  | To Do | Not Yet
Test_Integration | Integration test: record vitals → run AI → save record → alert appears for assigned doctor. | Iteration 3 | Quỳnh | Iteration 3 |  | To Do | Not Yet
Doctor_Dashboard | As a doctor, I want a dashboard showing appointmentQueue and completedRecords via DashboardServlet. | Iteration 3 | Nam | Iteration 3 |  | Done | Not Yet
Alert_ViewList | As a doctor, I want to view active notifications for my patients via NotificationService.findLatest. | Iteration 3 | Nam | Iteration 3 |  | Done | Not Yet
Alert_Resolve | As a doctor, I want to mark notifications as read/handled via NotificationService.markRead. | Iteration 3 | Nam | Iteration 3 |  | Done | Not Yet
Alert_ThresholdConfig | As a doctor, I want to receive alerts when glucose or hba1c is high via NotificationService.notifyMedicalRecordDiagnosisCompleted. | Iteration 3 | Nam | Iteration 3 |  | Done | Not Yet
Alert_UrgencyScore | Alert urgency scored by risk level + unresolved days to prioritise the doctor's queue. | Iteration 3 | Nam | Iteration 3 |  | Done | Not Yet
AI_FullTrendHistory | AI trend displays patient history of hba1c, glucose, and bmi across all visits. | Iteration 3 | Nam | Iteration 3 |  | Done | Not Yet
AI_SpecificDisease | Extend AI to predict which specific diabetic complications (neuropathy, nephropathy, retinopathy) the patient may develop. | Iteration 3 | Nam | Iteration 3 |  | Done | Not Yet
AI_ModelRetraining | Support model re-evaluation and retraining on new data; log the retraining process. | Iteration 3 | Nam | Iteration 3 |  | Done | Not Yet
Fix_FbsExangEncode | Fix database schema sync for hba1c and lipids (chol, tg, hdl, vldl) in Healthy_Record. | Iteration 3 | Nam | Iteration 3 |  | Done | Not Yet
Fix_PreprocessValidation | Add explicit validation in preprocess() of api_v2.py. | Iteration 3 | Nam | Iteration 3 |  | Done | Not Yet
Fix_AIServiceDown | Fix display when AI service is down — show risk_level = UNKNOWN gracefully. | Iteration 3 | Nam | Iteration 3 |  | Done | Not Yet
Fix_ModelPath | Fix hardcoded absolute Windows MODEL_PATH in api_v2.py for cross-platform deployment. | Iteration 3 | Nam | Iteration 3 |  | Done | Not Yet
Test_Authorization | Auth test: Doctor A cannot access records or run AI for Doctor B's patients. | Iteration 3 | Nam | Iteration 3 |  | Done | Not Yet
Test_AIEdgeCases | Test AI model with edge-case data: extreme age/vital values, many missing fields. | Iteration 3 | Nam | Iteration 3 |  | Done | Not Yet
Patient_ViewHistory | As a patient, I want to view my full medical history, diagnoses, and treatment records. | Iteration 3 | Đức Anh | Iteration 3 |  | To Do | Not Yet
Patient_ViewRiskResult | As a patient, I want to see my latest AI risk level and a simplified explanation. | Iteration 3 | Đức Anh | Iteration 3 |  | To Do | Not Yet
Patient_ViewAlerts_Detail | As a patient, I want to see alert details and which doctor is handling them. | Iteration 3 | Đức Anh | Iteration 3 |  | To Do | Not Yet
Patient_UpdateInfo_IT3 | As a patient, I want to update personal info with validation and confirmation. | Iteration 3 | Đức Anh | Iteration 3 |  | To Do | Not Yet
Test_UnitServices | Unit tests for ConsultationService and AIService (null fields, timeout, no prior history). | Iteration 3 | Đức Anh | Iteration 3 |  | To Do | Not Yet
Test_PatientPortal | End-to-end test of patient portal: view history, alerts, symptoms, update info. | Iteration 3 | Đức Anh | Iteration 3 |  | To Do | Not Yet
Note on H1: ====== ID#AAABjIWjVv0 KienNT (2025-05-12 09:11:37) Phân tích yêu cầu và thiết kế cho màn hình/chức năng được mô tả trong phần nào của tài liệu RDS?
Note on J1: ====== ID#AAABjIWjVvs kiennt (2025-05-12 09:11:37) Các nội dung update cụ thể, mô tả theo định dạng sau: dd/MMM-AccountName: Abc Xyz - dd/MMM: ngày thực hiện update (ví dụ 13/Oct) - AccountName: tài khoản của SV đã thực hiện update (ví dụ KienNT hoặc KienNTHe171209) - Abc Xyz: mô tả nội dung update
Note on K1: ====== ID#AAABjIWjVv4 kiennt (2025-05-12 09:11:37) Chức năng đã được update/bổ sung trong iteration nào sau khi được review
Note on C2: ====== ID#AAABjIWjVvo KienNT (2025-05-12 09:11:37) Level 1: 3-5 fields OR 2 trans Level 2: 6-7 fields OR 3 trans Level 3: 8-9 fields OR 4 trans Level 4: 10-11 fields OR 5 trans Level 5: 12-13 fields OR 6 trans Level 6: 14-15 fields OR 7 trans Level 7: >15 fields OR >7 trans

## Params
Screen/Function Complexity Levels
Screen complexity can be defined based on the screen's fields OR screen/function's transactions | Level | Fields | Trans* | LOC | Notes
- Transactions can be counted as number of transactions to the database or external systems/subsystems | Level 1 | 3-5 | 2 | 60
- Fields are screen's actionable components or database table fields; if there are some transactions those are | Level 2 | 6-7 | 3 | 90
not "related" to any fields, each of those transactions are counted as two fields and add those extra number | Level 3 | 8-9 | 4 | 120
to the total number of fields to define the screen/function complexity | Level 4 | 10-11 | 5 | 150
| Level 5 | 12-13 | 6 | 180
Some samples of screen complexity defining are as following | Level 6 | 14-15 | 7 | 210
Sample #1 | Level 7 | >15 | >7 | 240
*One trans (transactions) = Two fields (actionable screen components)
Sample #2
Sample #3